## enrique.bris
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
0 | NULL | As a Share user, I should be able to download any single asset with value of 'No' within the Usage Restrictions metadata field, regardless of other Usage Restrictions metadata values. | WBNU-75 | Story | 14400 | 14400 | 18885 | Delivered
Story | NULL | 0 | 28800 | 19978 | Delivered | A Share admin user should be able to create additional new users via "Manage App" section. | WBNU-507 | 75600
As an Upload Manager user, I want interactive paging on the main dashboard for optimized asset viewing and performance. | WBNU-436 | Story | 21600 | 20341 | Accepted | NULL | 36000 | 57600
As a Share user, I want to be able to use the browser 'Back' button to navigate between views within Dynamic Folders. | NULL | 144000 | 144000 | WBNU-437 | Story | 0 | 20714 | Delivered
As a Share user, I want to be able to navigate through Dynamic Folders via the breadcrumb trail links. | WBNU-105 | 33000 | 0 | Story | NULL | 0 | 20930 | Delivered
21144 | ToolBar Asset Search field should match other filter boxes - UI | 0 | NULL | WBNU-43 | Bug | Delivered | 7200 | 7200
WBNU-112 | Collection titles should have a max character limit of 25. | 600 | 22807 | Bug | Delivered | 1800 | 1200 | NULL
22834 | WBNU-101 | Bug | 14400 | 14400 | 0 | Back button does not function between Global Search and Share. | Delivered | NULL
As an Upload Manager user, I want a 'live update' on the dashboard after the following active user actions- upload, delete,reject, submit. | Story | NULL | Accepted | WBNU-438 | 93600 | 0 | 28800 | 22942
WBNU-433 | NULL | 0 | 23200 | Accepted | As an Upload Manager passive user, I want a notification to be presented if there has been assets added or deleted on my dashboard view. | Story | 1200 | 0
WS-1705 | 0 | 0 | Delivered | Display a modal with a form (file input & button) to allow the user to upload the desired file. | Sub-task | NULL | 0 | 23375
CLONE - OLD SHARE UI - As a Share user, I should be able to download any single asset with value of 'No' within the Usage Restrictions metadata field, regardless of other Usage Restrictions metadata values. | WBNU-416 | 0 | Finished | Story | NULL | 3600 | 3600 | 23716
OLD UI - A Share admin user should be able to create additional new users via "Manage App" section. | Story | 28800 | 24202 | Doing | WS-1750 | 0 | NULL | 28800
Merge branch 'WBNU-Ver-1-0' with latest Upload Manager UI/UX changes. | Sub-task | 0 | 24204 | Accepted | WBNU-509 | 22500 | NULL | 0
Bug | Auto Refresh not occurring on asset upload | Not Yet Started | 14400 | 14400 | NULL | 24581 | WBNU-529 | 0

## rita.lopez
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
Bug | 14400 | 14400 | 19129 | WE-1613 | Edit Request: Activity log not showing change in Project | Finished | 14400 | NULL
As a Walmart user, when I am performing bulk edits for users on requests the update/s takes a long time. | NULL | 0 | WE-1689 | Story | 0 | 0 | 19913 | Accepted
WE-1707 | 0 | Approve - New versions uploaded are still showing users assigned in "No Round" | Bug | NULL | 57600 | 57600 | 20155 | Accepted
21752 | Bug | Finished | 0 | NULL | WE-1865 | Excel autocorrect cause Unicode characters causing blank inserts | 14400 | 16200
Sub-task | 0 | 22966 | Change the action that opens the bulk edit modal from GET to POST | WE-1965 | NULL | 0 | 14400 | Accepted
Refactor bulk EDIT users to use a dynamically created SQL statement | WE-1966 | Sub-task | NULL | 28800 | 22967 | 0 | 28800 | Accepted
Refactor bulk ADD users to use a dynamically created SQL statement | WE-2083 | Sub-task | 0 | 14400 | 14400 | NULL | 23345 | Accepted
Refactor bulk REMOVE users to use a dynamically created SQL statement | WE-2084 | Sub-task | NULL | 14400 | 23346 | Accepted | 0 | 14400
Create a background job for send notifications for EDIT/ADD users | WE-2088 | Sub-task | NULL | 28800 | Accepted | 0 | 28800 | 23366
WE-2097 | NULL | 23500 | Sort Project and Request Name columns as integer instead of string | Chore | 28980 | 0 | 28800 | Not Yet Started
23565 | WE-2145 | Chore | Undefined INdex: manage_controller.php | 0 | NULL | Accepted | 0 | 0
23579 | Chore | PHP Warning: dbo_source.php | Accepted | NULL | WE-2159 | 0 | 0 | 0
23703 | Story | 7080 | WE-2190 | Improve performance of bulk edit users in Approve | Accepted | 0 | 0 | NULL
WE-2198 | Accepted | Request Queue is showing 'false' value in many request data fields. | Bug | 0 | NULL | 0 | 0 | 23747
WE-2217 | Sub-task | 0 | 0 | 23805 | Refactor bulk ADD users to use a dynamically created SQL statement | NULL | 0 | Accepted
WE-2218 | Sub-task | 0 | 0 | 23806 | Refactor bulk REMOVE users to use a dynamically created SQL statement | NULL | 0 | Accepted
23807 | WE-2219 | Sub-task | Accepted | 0 | 0 | 0 | Create a background job for send notifications for ADD users | NULL
Do not load unnecessaries model in the backend refactoring the front-end to send all necessary data | WE-2220 | Sub-task | NULL | 0 | 0 | 23808 | Accepted | 0
Users report feedback notes in Approve are appearing after save and then disappearing with no trace. | WE-2233 | 7200 | Bug | NULL | 0 | 0 | 23912 | Accepted
Accepted | As a user, when I am performing bulk edits in the drafts I receive an error. | WE-2250 | Bug | 9000 | NULL | 0 | 0 | 23949
23955 | Accepted | 12240 | NULL | WE-2255 | Bug | Manage App - Cannot add a new user | 14400 | 2700
24305 | WE-2306 | Chore | Finished | 28800 | 0 | 43500 | Move update numbers from walmart observer to individual actions | NULL
Investigate Pronto failure emails to find out if they work correctly | WE-2307 | Chore | 0 | 0 | Accepted | 1800 | NULL | 24309
24658 | NULL | WE-2335 | Bug | Request gets removed from Drafts when there are errors | Not Yet Started | 0 | 0 | 0
After submitting multiple drafts to queue, if some have errors then resubmitting attempts to send all requests again | 0 | NULL | 0 | 24659 | WE-2336 | Bug | 0 | Not Yet Started
24660 | WE-2337 | SMO drafts are being submitted without a Project selected | Not Yet Started | 0 | 0 | 0 | NULL | Bug

## josue
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
13892 | Bug | Accepted | 216000 | 216000 | NULL | WBNU-453 | Uploaded asset does not display without manual dashboard refresh | 0
Rejected assets display in Curator dashboard until browser manually refreshed. | WBNU-426 | Bug | 3600 | NULL | 0 | 3600 | 21154 | Accepted
WBNU-104 | Bug | 14400 | 14400 | 22877 | Keywords Filter Issue | Delivered | 0 | NULL
WE-2082 | Share - Search from Tags not displaying results | 0 | 23336 | Bug | Finished | 3600 | 300 | NULL
Creating a New Collection does not limit user to 25 character maximum. | WBNU-50 | 150 | 1800 | 23548 | Delivered | Bug | NULL | 1800
WS-1718 | Bug | Download Block is not functioning in Global Search | Accepted | 23605 | 3600 | 3600 | 0 | NULL
WBNU-365 | Not Yet Started | 0 | 23626 | Chore | Verify that walmart_qa_entities is configured properly | 0 | 0 | NULL
WBNU-100 | 0 | 600 | 23634 | Delivered | Share Keyword Filtering- keywords sometimes display multiple values in single instance | Bug | NULL | 600
0 | NULL | 7200 | As a Share user performing a global search, I want to be able to sort keywords result set alphabetically or by order of occurrence. | WBNU-102 | Story | 7200 | 23635 | Delivered
Story | 0 | 3600 | CLONE - As a Walmart Stores external Vendor, I want login credentials and access to Upload Manager only. | WBNU-411 | NULL | 3600 | 23711 | Finished
23712 | WBNU-412 | Story | CLONE - Share/UM new user sub group- Upload/View | Finished | 3600 | 3600 | 0 | NULL
3600 | Finished | CLONE - Share/UM new user type (for every main group)- Upload Manager Only | WBNU-413 | Story | 0 | NULL | 3600 | 23713
WBNU-414 | NULL | 3600 | 23714 | CLONE - Share/UM new user sub group (for every main group)- View Only | Story | 0 | 3600 | Finished
Story | NULL | 7200 | 23715 | CLONE - OLD SHARE UI - As a Share user, I shouldn't be able to create an external link containing any single assets that have a 'Usage Restrictions Commence Date' that has past. | WBNU-415 | 0 | 7200 | Finished
Bug | 0 | 14400 | 23717 | Finished | CLONE - 'Usage Restrictions Details' field not transferring from Upload Manager to Share. | WBNU-417 | NULL | 14400
WBNU-455 | Epic | 0 | 0 | 0 | NULL | 23834 | RealTIME Video Processing Enhancements | Doing
Users are unable to delete empty folders using the " Delete Folder" functionality". | Bug | 600 | 0 | WS-1743 | NULL | 0 | 23906 | Delivered
Not Yet Started | 0 | NULL | 23908 | WBNU-451 | Epic | Share Global Folders Drag & Drop | 0 | 0
1800 | 1800 | Accepted | Create a list of RealTIME supported file formats and codecs for Upload Manager/Share video uploading. | WBNU-458 | Chore | NULL | 3600 | 23932
24112 | Epic | Not Yet Started | 0 | NULL | WBNU-486 | Upload Manager Notifications | 0 | 0
24132 | Epic | Share External Links Enhancements | 0 | 0 | NULL | WBNU-492 | Doing | 0
As a Walmart Stores Share external user, I want to be able to select individual assets within external links. | Story | 0 | 0 | 24133 | Not Yet Started | WBNU-493 | NULL | 0
As a Walmart Stores Upload Manager Vendor, I want an email notification sent to me when my assets are done processing. | WBNU-499 | Story | 0 | NULL | 0 | 0 | 24139 | Not Yet Started
24403 | 0 | NULL | WBNU-523 | Epic | Merging Namespace Codebase with WS new Share UI codebase. | Not Yet Started | 0 | 0
Truncate Walmart Stores 'Project' table and import data from provided CSV file into 'Project' table. | WS-1759 | Chore | 0 | 0 | NULL | 0 | 24656 | Not Yet Started

## jamar.walker
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
WE-1675 | Accepted | As a user, when in Share I would like the versions that are displayed renamed. | Story | 0 | NULL | 7200 | 7200 | 19707
22954 | Sub-task | Delivered | 0 | 0 | NULL | TLIMIT-745 | Create New Endpoint /services/track/kits | 0
Bug | Accepted | 0 | 1800 | 23556 | WE-2136 | Displaying wrong number of assets | 0 | NULL
WE-2140 | Chore | timemanage/attachment.ctp PHP Notice ln 63 | 0 | 0 | 0 | 23560 | Accepted | NULL
WE-2143 | Chore | PHP Notice milestones_and_supporting_documents.ctp | 0 | 0 | NULL | 23563 | Accepted | 0
23566 | WE-2146 | Chore | 0 | 0 | Undefined Index: realtime_event_project_updated.php | Accepted | 0 | NULL
23574 | Chore | Job QUEUE_DOWNLOAD:send_download_assets_link FAILED | 28800 | NULL | WE-2154 | Accepted | 28800 | 0
WE-2156 | Finished | 14400 | 10500 | 23576 | Bug | Manage - Linked Assets does not work | 3900 | NULL
Bug | Accepted | 0 | 23578 | WE-2158 | getDashboardProjectTree() warning | 0 | 0 | NULL
WE-2178 | Bug | 0 | NULL | If user creates two requests in "Drafts" tab for same project and "Deletes" one of that draft App deletes both at same time in Manage. | 0 | 0 | 23607 | Accepted
14400 | 23625 | Finished | When dashboard is grouped, groups with ampersand displays as &amp; | WE-2186 | Bug | NULL | 0 | 14400
WE-2187 | 21600 | 0 | 14400 | 23628 | If the user does not enter a priority on a request, when the request is displayed on the dashboard, '&npsp;' is displayed on the dashboard | Bug | NULL | Finished
PHP Notice: Undefined index: AmUser in /var/www/vhosts/deploy/walmart/app/vendors/realtime/lib/RealTime/Events/realtime_event _project_updated.php on line 9 | Chore | 0 | NULL | 0 | 0 | Accepted | WE-2194 | 23742
23744 | WE-2196 | Bug | Update Project Event is not taking the user_id. | Accepted | 0 | NULL | 14400 | 14400
Bug | 9660 | NULL | 0 | 23839 | Accepted | Project search filter in LHN on Manage default view does not work. | WE-2229 | 0
23938 | Share Delete Assets - cannot delete multiple assets | Accepted | 0 | 45000 | NULL | WE-2242 | Bug | 0
24149 | 14400 | 0 | 21600 | WE-2280 | Chore | Share - do not display deleted assets | Accepted | NULL
When I attempt to bulk submit requests from the draft tab, all selected requests are not removed from the UI. | WE-2289 | 30960 | NULL | 0 | 24175 | Accepted | Bug | 0
24323 | WE-2310 | Chore | NULL | Manage - Optimize LHN filter | Finished | 0 | 0 | 14400
when approving a request to request queue the please wait loading screen hags | WE-2316 | Bug | 50400 | Accepted | NULL | 0 | 21600 | 24400
WE-2321 | Bug | NULL | In Manage, requests that are moved to other groups don't get "checked" when the group is checked | 0 | 28800 | 28800 | 24558 | Doing

## kreatetechnology
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
18907 | CP-104 | Bug | Item showing incorrect location | 14400 | 14400 | NULL | Not Yet Started | 0
As a user I will be able to play a video by calling the play() function | CP-17 | 0 | Story | 0 | NULL | 0 | 20121 | Accepted
Story | 0 | 20123 | CP-16 | A video player shall not have any controls. | Accepted | 0 | 0 | NULL
20124 | Server side video details | Accepted | 0 | 0 | NULL | CP-18 | Story | 0
CP-2 | move the catalog database to use RDS | 7200 | 0 | 20601 | Chore | Accepted | 7200 | NULL
20603 | CP-3 | 28800 | 0 | Chore | upgrade catalog server | Accepted | 28800 | NULL
20617 | CP-4 | Relocate walmart merchtrak | 14400 | 0 | NULL | Chore | Not Yet Started | 14400
CP-7 | Not Yet Started | 28800 | NULL | 20631 | Chore | Application and Development Security training | 28800 | 0
20635 | Bug | 0 | CP-11 | Change password link is not working | Accepted | 0 | 0 | NULL
CP-34 | Story | 0 | NULL | 7200 | 7200 | 21157 | RIT > THIS TICKET IS FOR RIT! Add the users in the description to the RIT system. New Users need to be added to the RIT Share Module. | Accepted
Accepted | 0 | NULL | 21360 | CP-15 | Bug | Browser interoperability | 0 | 0
CP-14 | Accepted | 0 | NULL | 21361 | Bug | Black box appearing at the start of the video. | 0 | 0
22699 | Bug | Accepted | 10800 | CP-791 | Daily file confirmation email | 0 | 0 | NULL
22841 | CP-796 | Accepted | 0 | Bug | Research what it would take to fix ticket number CP-104 | 0 | 0 | NULL
CP-806 | Chore | Remote AD not pointed to correct IP address | Accepted | NULL | 23355 | 0 | 0 | 0
CP-813 | Epic | 0 | 0 | 0 | NULL | 23962 | RemoteAD is not streaming video and/or screenshots | Not Yet Started
23965 | CP-814 | Bug | Not Yet Started | 0 | 0 | 0 | RemoteAD does not stream client desktop | NULL
CP-822 | Bug | Cannot upload images on new catalog server | 3600 | 24404 | Accepted | 3600 | 0 | NULL
CP-823 | Cannot view new catalogs | Accepted | 0 | 0 | 24550 | Bug | 0 | NULL
Product overlays do not show up in Safari | Finished | 14400 | 24579 | CP-825 | Bug | 10800 | 3600 | NULL
CP-828 | 0 | 0 | 24588 | NULL | Bug | Chicos - Items on shot list not appear appearing in TimeTrack | Doing | 0

## susana.kaiser
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
13000 | Story | Improve the performance of bulk ticket update. | WE-1353 | Accepted | 0 | 0 | 0 | NULL
WE-1691 | Story | 19926 | As a Walmart user, when I make changes to requests in the Draft Tabs I would like the changes to take affect immediately. | 0 | NULL | 0 | 0 | Accepted
As a Walmart user, when I am performing bulk edits on request fields the update/s takes a long time. | 0 | NULL | Accepted | WE-1947 | Bug | 3600 | 3600 | 22886
Bulk Request Update - Build dynamic SQL statement for am_ticket fields | WE-1955 | 0 | NULL | 28800 | 22920 | Accepted | Sub-task | 28800
28800 | Accepted | Bulk Request Update - Build dynamic SQL statement for dynamic fields | WE-1956 | Sub-task | 0 | NULL | 28800 | 22922
22923 | WE-1957 | Bulk Request Update - Trigger the ticket update event in bulk | 28800 | 28800 | NULL | Sub-task | Accepted | 0
WE-1958 | Sub-task | 0 | NULL | 28800 | Accepted | Bulk Request Update - Build dynamic SQL statement for custom dashboard tables | 28800 | 22926
23523 | Refactor /manage/update_datatable_index | Accepted | 0 | 0 | NULL | WE-2114 | Chore | 0
PHP Warning: array_filter() expects parameter 1 to be array, boolean | WE-2147 | Bug | NULL | 0 | 23567 | Accepted | 0 | 0
23568 | Bug | 14400 | 0 | 25200 | WE-2148 | Undefined index: manage_controller.php | Accepted | NULL
Accepted | 7200 | 21600 | NULL | 23577 | WE-2157 | Chore | Undefined index: realtime_event_ticket_updated.php | 0
0 | NULL | 0 | Accepted | PHP Fatal error: Call to a member function users() on a non-object in /var/www/vhosts/deploy/walmart/app/jobs/process_send_notification.php on line 389 | WE-2192 | Chore | 0 | 23735
NULL | 2700 | 23868 | Finished | On the project detail page, do not show link to drafts if the user has none for the project | WE-2230 | Bug | 11700 | 14400
Requests in Request Queue that are accepted by Producer are not leaving Request Queue as expected. | WE-2234 | NULL | 0 | 23913 | Bug | 23880 | 0 | Accepted
In Share in single asset view "Previous" and "Next" arrows get disappear after refreshing web page. | Bug | 23942 | Accepted | WE-2246 | 27000 | NULL | 0 | 0
Bug | Accepted | NULL | 23957 | WE-2256 | Color Coding Requests in the Dashboard causes error | 0 | 0 | 25200
24042 | WE-2274 | Chore | Code clean up for creating round users | Finished | 14400 | 0 | 21600 | NULL
24128 | WE-2277 | Sub-task | 0 | Investigate how redis session is created | Finished | 0 | 0 | NULL
Finished | 0 | 24129 | WE-2278 | Sub-task | Investigate login process | 0 | 0 | NULL
Sub-task | Investigate how Redis session data is fetched | Finished | 0 | 0 | 0 | NULL | 24130 | WE-2279
NULL | Accepted | As a User when I upload a CSV file to create tickets the Category / Department is not populated. | WE-2283 | Bug | 1500 | 3600 | 3600 | 24156
WE-2288 | Bug | "Actions" column on the Request Queue Dashboard is not showing all the correct data. | 3600 | NULL | 0 | 0 | 24174 | Accepted
Bug | Manage App - getting undefined error editing milestones | 14400 | 1200 | 24573 | WE-2330 | Doing | 14400 | NULL

## arturo.mejia
Title | Key | Type | Time Spent | Project | Remaining Estimate | Original Estimate | ID | Status
As a Share user, I want the "TaggingJS" plugin implemented for a more intuitive process for entering asset keywords. | WBNU-332 | Story | 18300 | 0 | 14400 | NULL | 20476 | Delivered
NULL | 0 | 14400 | 20823 | As a Share user, when attempting to download assets that have usage restrictions tied to them, I want a download request process to commence. | WBNU-78 | Story | 36000 | Delivered
As an Upload Manager user, I want ASF video files converted to WMV files when uploaded and processed. | WBNU-434 | 9600 | Accepted | Story | NULL | 0 | 3600 | 20902
Action item menu options from center pane displaying intermittently. | WBNU-113 | 0 | 22805 | Bug | NULL | 10800 | 10800 | Rejected
NULL | 3600 | User should be able to edit both 'Name' field and 'Description' field within right hand side 'Info' panel. | WBNU-111 | Bug | 0 | 3600 | 22809 | Delivered
As a Walmart Stores user, I want to be able to update UM/Share asset metadata by uploading a pre-formatted spreadsheet. | WS-1689 | 0 | Story | NULL | 72000 | 72000 | 23138 | Accepted
WS-1734 | NULL | 23324 | Accepted | Move all assets within client provided spreadsheet to Share from Upload Manager. | Chore | 32400 | 3600 | 3600
0 | 0 | 23374 | Finished | Convert existing cake shell "shareum_import_metadata" to a background job. | WS-1704 | Sub-task | NULL | 0
WS-1706 | NULL | 0 | Accepted | On file upload, the file is sent to the background job for process and importing status updates will be displayed to the user. | Sub-task | 0 | 0 | 23376
Action item menu options from center pane disappear after Global Search. | 0 | 14400 | 14400 | Delivered | WBNU-23 | Bug | NULL | 23505
WS-1744 | 3600 | 3600 | 0 | NULL | 23611 | Chore | Indesign files to be reprocessed. | Doing
23615 | As a Share user, in multi-asset view, I want to be able to select multiple folders at once with the Shift key. | WBNU-92 | Story | 360 | NULL | 6840 | 7200 | Delivered
Research why video uploads are failing through Upload Manager and Share. | 10800 | 23619 | Accepted | WS-1721 | Bug | 0 | NULL | 10800
Review & investigate why values are still shown with comma groups. | Sub-task | NULL | 23705 | Not Yet Started | WBNU-109 | 0 | 0 | 0
WBNU-110 | Sub-task | Fix the comma group issue on Keywords list. | 0 | NULL | 23706 | Not Yet Started | 0 | 0
23740 | WS-1735 | Bug | Doing | 7200 | Walmart Stores> Videos are not playing back. | 7200 | 7200 | NULL
23813 | Chore | 1800 | 900 | WBNU-446 | Walmart Stores> New User Creation | Accepted | 900 | NULL
1800 | 900 | NULL | 23814 | WBNU-447 | Story | New User Creation- David Orosco | Accepted | 900
Story | 0 | NULL | 3600 | Delivered | Walmart Stores> Change a group of one user to match another users group. | WBNU-461 | 3600 | 23837
23907 | WBNU-450 | Cleanup existing Keywords with commas via a script. | Finished | 3600 | NULL | Chore | 3600 | 0
Chore | Create and Execute scripts to clean up Usage Restrictions data. | Delivered | 14400 | 24111 | WBNU-485 | 7200 | 7200 | NULL
As a Walmart Stores Share external user, I want the asset thumbnails to have a caption of 'Title' field rather than 'Filename' field. | NULL | 3600 | Delivered | WBNU-494 | Story | 2400 | 1200 | 24134
NULL | 7200 | Finished | As a Walmart Stores Share external user, I want there to be a 'Select All' checkbox on external link pages. | WBNU-495 | Story | 7200 | 0 | 24135
As a Walmart Stores Share external user, I want to download only the selected items when I click 'Download Items' button from external links page. | Story | 21600 | 24136 | WBNU-496 | NULL | 0 | 14400 | Finished
14400 | As a Walmart Stores Share external user, I want the contact sheet to be generated with selected assets only. | WBNU-497 | Story | NULL | 0 | 14400 | 24137 | Finished
WBNU-498 | NULL | 3600 | As a Walmart Stores Share external user, I want the asset thumbnails on the downloaded contact sheet to have a caption of 'Title' field rather than 'Filename' field. | Story | 3600 | 0 | 24138 | Finished
24144 | Bug | Share filter in multi-asset view not functioning. | 3600 | NULL | WS-1745 | Delivered | 3600 | 0
Walmart Stores> New Users need to be added to Walmart. | 1800 | NULL | 24183 | WS-1748 | Bug | Accepted | 1800 | 0
24307 | WS-1751 | Chore | Walmart Stores>Add New Users | 2400 | 1200 | Accepted | 3600 | NULL
24318 | WS-1752 | Fix process that generates InDesign previews | 10800 | Sub-task | Delivered | 10800 | 0 | NULL
Bug | 3600 | 1200 | 24331 | WS-1754 | Walmart Stores> Add new user | Accepted | 2400 | NULL
24336 | WS-1755 | Bug | 14400 | 14400 | 0 | Revert asset metadata changes on 11/25. | Doing | NULL
CLONE (Old UI)- Create a throttled job queue for all video processing jobs. | NULL | 3600 | 3600 | 24343 | WS-1756 | Chore | 0 | Delivered
24562 | Sub-task | Allow a user to select individual assets. | 7200 | 14400 | WBNU-525 | Finished | 0 | NULL
24580 | Chore | Merge background jobs | 0 | 0 | WBNU-528 | Not Yet Started | 0 | NULL